## Excel Gantt Chart
Gantt Chart
START DATE | END DATE | DESCRIPTION | PAPER OUTPUT | DURATION (days)
2018-10-25 | 2018-11-30 | Stage 1 | No | 35
2018-11-30 | 2018-12-30 | Stage 2 | No | 30
2019-01-01 | 2019-03-01 | Stage 3 | Yes: ENASE, SACI | 60
2019-03-01 | 2019-09-01 | Stage 4 | No | 180
2019-09-01 | 2020-02-01 | Stage 5 | Yes: ICSME | 150
2020-02-01 | 2020-07-01 | Stage 6 | Yes: ENASE | 150
2020-07-01 | scientific report nr. 1 with the intermediate results of the research
2020-06-01 | 2021-01-01 | Stage 7 | Yes: ICSE | 210
2020-12-01 | 2021-05-01 | Stage 8 | No | 150
2021-05-01 | scientific report nr. 2 with the intermediate result of the research
2021-09-01 | doctoral thesis completion
1

## Excel Timeline Template
Excel Timeline Template
Enter Your Project Details Here
DATE | DESCRIPTION | POSITION
2019-03-01 | Stage 3: Paper ENASE | 1
2019-03-01 | Stage 3: Paper SACI | 2
2020-02-01 | Stage 5: Paper | 3
2020-07-01 | Stage 6: Paper | 4
2021-01-01 | Stage 7: Paper | 5
`
Make beautiful timelines in PowerPoint for important meetings. |  |  | Instantly turn Excel data into PowerPoint slides with the Office Timeline add-in for PowerPoint.
www.officetimeline.com
https://www.officetimeline.com/download
Note on D6: Excel Project Timeline Tip: The position values vary the height of your Milestones and are used to prevent text overlap. Using negative numbers will place Milestones labels below the timeband. If you position a Milestone below the timeband click on its label in the chart to set its Label Position to below.
Note on B17: Excel Project Timeline Tip: To add more Milestones, insert new rows into this table and then use the Select Data field to update your Series as shown in step # 3 here: https://www.officetimeline.com/make-timeline/excel
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download the Free Office Timeline plug-in for PowerPoint - 14-day Free Trial.
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of PowerPoint.
Copy your Excel table and paste it into Office Timeline with the PASTE button.
3. Click the green SAVE button to instantly produce your timeline slide.